## Instructions
Benefits Realisation Plan Template
A practical plan for governing expected benefits from business case through operational review.
How to use this workbook
1. Start with a benefit | State the change for a beneficiary, not a deliverable or activity.
2. Set a baseline | Record the starting value, method, date, source, and assumptions before the intervention distorts the comparison.
3. Name owners | The benefit owner is accountable for realisation; measurement and intervention owners may be different people.
4. Link dependencies | State the operational, behavioural, technical, policy, or commercial conditions that must hold.
5. Plan reviews | Define when performance is reviewed, who acts on a variance, and the decision route.
6. Retire honestly | Record benefits that are delayed, changed, disbenefits, or retired—and the authority that made the decision.
Included example | The Benefits Plan sheet contains a fictional example for a self-service claims service. Replace or delete it before use.
Source and limits | The template is Strategica synthesis based on public benefits-management guidance. It is not a substitute for finance, legal, regulatory, safety, procurement, or organisational governance requirements.

## Benefits Plan
Benefits Realisation Plan
One row per expected benefit or disbenefit. Use the review fields to govern value after handover, not just project delivery.
ID | Benefit / disbenefit | Beneficiary | Benefit hypothesis | Benefit owner | Measurement owner | Measure | Baseline | Baseline date | Target | Target date | Evidence / source | Key dependencies and assumptions | Intervention / change required | Review cadence | Current performance | Status | Next decision or action | Decision owner | End condition / retirement rule
EX-001 | Claims applicants complete eligible claims without assisted contact (benefit) | Eligible claimants and service operations | If the online claim journey makes eligibility and evidence requirements clear, more applicants will complete a valid claim without calling support. | Head of Claims Operations | Service Performance Analyst | Share of eligible claims completed without assisted contact | 52% | 2026-07-01 | 70% | 2027-03-31 | Service analytics; assisted-contact records; research sample | Identity service uptime; policy wording approval; staff training; eligible-claim definition remains stable | Redesign eligibility guidance, evidence upload, and recovery route; train service agents | Monthly during delivery; quarterly after handover | Not yet measured | Planned | Approve first operational baseline after beta; review if completion remains below 60% after two months | Service owner within delegated operating tolerance; sponsor for benefit-target change | Retire when benefit reaches target for two consecutive quarters, is re-baselined with approval, or is formally retired with rationale